## Priority Model
ITS PROJECT REQUEST PRIORITIZATION MODEL
| Strategy/ Objective | Criteria | Condition | Selection
Urgency (40) | Strategic Goal (10) | How does this project align with UTHSC's strategic mission and goals or the Chancellor's specific goals for ITS? | (Select best one only) | (Mark Y next to one only)
Directly supports a goal
Increases effectiveness and efficiency
No strategic goal directly supported
| Requirement (10) | Is this project required? | (Select best one only) | (Mark Y next to one only)
Yes, to fulfill government mandate (ex., HIPAA) or SACS requirement
Yes, to fulfill mandate from UTHSC administration, UT system administration, collegiate accrediting agency, or similar group
Yes, to reduce institutional cost
No
| Need of System (10) | Is this an urgent or pressing need? | (Select best one only) | (Mark Y next to one only)
Urgent for university as a whole (most colleges and administrative units)
Urgent for 2-3 colleges or administrative units
Urgent for 1 college or administrative unit
Urgent for 1 group within a college or administrative unit
Not urgent
| Flexibility (10) | What is the desired project delivery timeline? | (Select best one only) | (Mark Y next to one only)
≤ 3 months
4-6 months
7-12 months
> 12 months
Impact (35) | Reach (7) | How many users will be impacted? | (Select best one only) | (Mark Y next to one only)
Improvement for user and provider (+9 pts)
Improvement for user OR provider (+6 pts)
No improvement for user and provider (-2 pt)
51-500 (+3 pts)
< 50 (+1 pt)
1,001+ people
101-1,000 people
25-100 people
< 25 people
| Positive Outcomes (7) | How does the project improve the ability of the customers/end users to do their tasks or affect staff resources? | (Select best one only) | (Mark Y next to one only)
Enables customer to meet mandate
Eliminates redundancy (ex., data double-entry) and/or significantly increases efficiency (ex., reduces physical paper storage or paper workflows, facilitates accurate reporting, etc.) for customer
Reduces number of staff hours or systems needed to complete task for ITS but not for customer
No effect on number of staff hours or systems needed to complete task for either customer or ITS
Additional staff/systems needed for support
| Current State (7) | What is the state of the current system? | (Select best one only) | (Mark Y next to one only)
Unsecure or unsupported/end of life
Functioning, but close to end of life
Functioning, but inefficient
Functioning securely and efficiently, but upgrade is available
No current system/not applicable
| Implications of Not Implementing (5) | What are the implications if this project is NOT implemented? | (Select best one only) | (Mark Y next to one only)
Campus safety implications
Financial or legal implications (ex., loss of revenue, etc.)
Information security implications
Lack of efficiency
No tangible negative effects
| Dependency (5) | What is the impact of this project on other ongoing, planned, or near-term projects? | (Select best one only) | (Mark Y next to one only)
Major impact (ex., Must be completed before another major project can begin or finish)
Moderate impact (ex., Is positively affected by another project's outcomes
Little to no impact
Duplicates the results of another project that is already approved, in progress, or completed
| Negative Outcomes (4) | Does the project have any potentially significant (but surmountable) anticipated negative risks? | (Select best one only) | (Mark Y next to one only)
No significant negative outcomes anticipated
One significant negative outcome anticipated
Multiple significant negative outcomes anticipated
Financials (15) | Cost (5) | What are the known costs (rounded to nearest dollar)? | (Select best one only) | (Mark Y next to one only)
No direct costs anticipated at this time
Direct costs anticipated but unknown at this time
< $5,000
$5,000 - $9,999
$10,000 - $24,999
25,000 - 49,999
$50,000 - $99,999
≥ $100,000
| Cost Planning (5) | Have funds already been approved or set aside for the project? | (Select best one only) | (Mark Y next to one only)
No direct costs anticipated at this time
Yes, as part of this fiscal year’s budget
Yes, as part of next fiscal year’s budget
No, but approval has been given for the project
No, and the project has not yet been approved
| Operational Cost (5) | What is the project's return on investment (ROI)? | (Select best one only) | (Mark Y next to one only)
Will pay for itself and generate cash
Will pay for itself but not generate cash
Will save money
No tangible financial ROI
Complexity (10) | Complexity (10) | What is the anticipated level of complexity of the project's development/implementation work? | (Select best one only) | (Mark Y next to one only)
No complexity, very simple (will require resources from 1-2 ITS departments for < 1 month)
Low complexity (will require resources from 1-2 ITS departments for 1-3 months
Medium complexity (will require resources from 1-3 ITS departments for 3-6 months
High complexity (will require resources from 2+ ITS departments for > 6 months)
Overly complex and potentially unachievable at this time

## Mandatory Codes
Mandatory Requirements: | Y - UR | University Requirement
| Y - BT | Board of Trustees Requirement
| Y - SR | State Requirement
| Y - FR | Federal Requirement
| Y - A | Audit Requirement
| Y - S | Supportability Requirement (End of Life)
| Y - T | Tech Fee Proposal Requirement